## Sheet1
2010 Standard Specifications
Type of Certification | Specification Section | LINK | Who Provides it | Who Gets it | When is it due | QPL/APL Requirement | LINK | Lims Entry
Division I Specifications
Sublet Certification | 4-3.2.2 | Link | Subcontractor | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=4-3.2.2
Special Erection Equipment | 5-1.5.1 | Link | Specialty Engineer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=5-1.5.1
Falsework and Shoring Requiring Shop Drawings | 5-1.5.2 | Link | Specialty Engineer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=5-1.5.2
Temporary Formwork | 5-1.5.3 | Link | Specialty Engineer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=5-1.5.3
Cetificate of Claim | 5-12.9 | Link | Contractor | Engineer | Upon request | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=5-12.9
Producer Certification (QPL) | 6-1.3.1 | Link | Producer | Engineer | Before Material Used | QPL |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=6-1.3.1
Contractor Installation Certification (APL) | 6-1.3.2 | Link | Contractor | Engineer | After installation | APL | Link |  | http://www3.dot.state.fl.us/trafficcontrolproducts/ | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=6-1.3.2
Source of Supply Steel | 6-5.2 | Link | Producer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=6-5.2
Enviromental Certification | 7-1.1 | Link | Contruction Industry Licensing Board | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=7-1.1
Agricultural Certification (sod,hay, straw, mulch) | 7-1.3 | Link | F.D. of Agriculture/Plant Division | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=7-1.3
Sublet Certification | 8-1 | Link | Contractor | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=8-1
Manufacturers Certification (truck requirement) | 9-1.5 | Link | Contractor | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=9-1.5
Certification of Payment to Subcontractors | 9-5.6 | Link | Contractor | Engineer | Before final payment | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=9-5.6
Division II Specifications
Portable Changeable (Variable) Message Sign(PCMS) | 102-9.9 | Link | Manufacturer | Engineer | Prior to use | APL | Link |  | http://www.dot.state.fl.us/specificationsoffice/ProductEvaluation/QPL/QPLMOTIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.9
Portable Regulatory Sign Certification | 102-9.10 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www.dot.state.fl.us/specificationsoffice/ProductEvaluation/QPL/QPLMOTIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.10
Radar Speed Display Unit | 102-9.11 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 102 Maintenance of Traffic&QPLDesc=Radar Speed Display Unit&QPLNum=S102 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.11
Temporary Traffic Control Signals | 102-9.12 | Link | Manufacturer | Engineer | Prior to use | APL | Link |  | http://www3.dot.state.fl.us/trafficcontrolproducts/ | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.13
Safety Warning Transmitter | 102-9.13 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www.dot.state.fl.us/specificationsoffice/ProductEvaluation/QPL/QPLMOTIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.12
Trucks and Truck Mounted Impact Attenuators | 102-9.14 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www.dot.state.fl.us/specificationsoffice/ProductEvaluation/QPL/QPLMOTIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-9.14
Contractor's Certification of Quantities | 102-12.2 | Link | Contractor | Engineer | After placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=102-12.2
Preconstruction Requirements(Contractor's Erosion control plan) | 104-5 | Link | Contractor | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=104-5
Artificial Coverings (Erosion control balnkets) | 104-6.4.11.1 | Link | Contractor | Engineer | Upon placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=104-6.4.11.1
PCI Certification | 105-3.4 | Link | Prestress Concrete Plant | Engineer | Before Operation | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-3.4
AISC Certification | 105-3.5 | Link | Contractor | Engineer | Before Operation | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-3.5
Notarized Certification of Compliance | 105-4 | Link | Contractor | Engineer | Monthly/before final payment | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-4
Concrete Production Facility Mgr of QC | 105-8.7.4 | Link | Facility Manager | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-8.7.4
Eng'r. Proof of License or Certification | 105-8.8.2 | Link | Supervisory personnel-bridge structures | Engineer | Pre-construction conference | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-8.8.2
Experience Record | 105-8.8.3 | Link | Supervisory personnel | Engineer | Pre-construction conference | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-8.8.3
Prestressed Concrete Plant Facility QC Personnel | 105-8.9 | Link | Facility Manager | Engineer | Prior to work | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-8.9
Signal Installation Certification | 105-8.10 | Link | Contractor | Engineer | Prior to work | APL | Link |  | http://www3.dot.state.fl.us/trafficcontrolproducts/ | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=105-8.10
Certification of Compliance (hazardous/waste) | 110-9.5.2 | Link | Contractor/firm hauling the hazardous waste material | Engineer | Upon request/ After transport done | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=110-9.5.2
Geosynthetic reinforcement | 145-5 | Link | Supplier | Engineer | At least 10 days prior to placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=145-5
Certification of Quantities (Superpave Asphalt Base pay item) | 234-9 | Link | Contractor | Engineer | No later than 12 O'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=234-9
Delivery Certification (Batch Adjustment) | 288-3.3 | Link | Contractor | Engineer | Prior to unloading at the site | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=288-3.3
Delivery Certification (Cement Treated Permeable Base) | 288-3.4 | Link | Contractor | Engineer | Prior to unloading at the site | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=288-3.4
Certification of Calibration (Calibration of Tanks for tack coats) | 300-9.2 | Link | Contractor/distributor | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=300-9.2
Certification of Quantities (Superpave Asphalt Concrete pay item) | 334-7 | Link | Contractor | Engineer | No later than 12 O'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=334-7
Testing and Certification Requirements(asphalt rubber binder production) | 336-5 | Link | Contractor | Engineer | Upon Deliver | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=336-5
Pre treated Aggregate for FC- Certification | 337-9.3.3 | Link | Contractor | Engineer | with each load of material delivered to the HMA plant | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=337-9.3.3
Certification of Quantities (Asphalt concrete friction course pay item) | 337-11 | Link | Contractor | Engineer | no later than 12 o'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=337-11
Certification of Quantities (Miscellaneous asphalt pavement pay item) | 339-7 | Link | Contractor | Engineer | no later than 12 o'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=339-7
Certification of Quantities for Bituminous Material | 341-9.3 | Link | Contractor | Engineer | no later than 12 o'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=341-9.3
Certification(Concrete mix design for precast/prestressed concrete) | 346-3.4 | Link | Contractor | Engineer | prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=346-3.4
Certification (Chloride Content) | 346-4.2.2 | Link | Contractor | Engineer | After production/ placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=346-4.2.2
Delivery Certification (Concrete) | 346-6.3 | Link | Batcher | Engineer | On delivery per batch of concrete before unloading at the placement site | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=346-6.3
Certification (Small Quantities of Concrete) | 346-9.6 | Link | Contractor | Engineer | After placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=346-9.6
Certification and Acceptance (Portland Cement Concrete-Class I/ non-struc.) | 347-5 | Link | Contractor/Batcher | Engineer | On Delivery | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=347-5
Certification (Composition of Concrete-Concrete Pavement Slab replacement) | 353-3.2 | Link | Batcher | Engineer | On delivery per batch of concrete before unloading at the placement site | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=353-3.2
Certification (Materials) | 400-5.7.3.3 | Link | Contractor | Engineer | Upon delivery to jobsite. | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=400-5.7.3.3
Materials Test and Certification finish coating (Finishing Concrete../Concrete Structures) | 400-15.2.6.6 | Link | Contractor/Manufacturer | engineer | before any portion of any shipment of finish coating is applied on the project | QPL | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 400 Concrete Structures&QPLDesc=Applied Finish Coating&QPLNum=S400 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=400-15.2.6.6
Manufacturer's Certification (Sealing Cracks & Concrete Structure Surfaces-Penetrant Sealant) | 413-2.4.2 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=413-2.4.2
Manufacturer's Certification (Shelf life-manomer) | 413-3.2.2. | Link | Contractor/Manufacturer | Engineer | prior to transporting the material to the job site | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 413 Sealing Cracks and Concrete Structure Surfaces&QPLDesc=High Molecular Weight Methacrylate (HMWM)&QPLNum=S413 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=413-3.2.2.
Manufacturer's Certification (Trench Drain System) | 436-2 | Link | Contractor/Manufacturer | Engineer | Upon placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=436-2
Manufacturer's Certification (Precast Concrete Drainage Products) | 449-2 | Link | Contractor/Manufacturer | Engineer | Upon placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=449-2
Product Certification (Precast Prestressed Concrete Construction/QC-QA Program) | 450-2.3 | Link | Contractor | Engineer | Each monthly request for payment | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=450-2.3
Manufacturer's Certification (Precast Prestressed Concrete Construction/Strand nChucks and Splice Chucks) | 450-3.2 | Link | Contractor/Manufacturer | Engineer | Upon use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=450-3.2
Certification (Sidewalk Cover Plate) | 458-2.4 | Link | Contractor/Manufacturer | Engineer | prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=458-2.4
Structural Steel & Misc. Steel (Member or Componenet Certification) | 460-4.7 | Link | Contractor | Engineer | At least one a month | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=460-4.7
Certification (Slip critical classification) | 460-5.4.2 | Link | Contractor | Engineer | prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=460-5.4.2
Manufacturer's Written Certification (Multirotational Bearings) | 461-4 | Link | Contractor/Manufacturer | Engineer | upon installation | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=461-4
Manufacturer's Certification (Shear Connectors) | 502-2.6 | Link | Contractor/Manufacturer | Engineer | prior to purchase | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=502-2.6
Manufacturer's Certification (in-plant QC test reports ) | 502-3.4 | Link | Contractor | Engineer | upon request | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=502-3.4
Manufacturer's Certification (Expansion fitting) | 510-7.5 | Link | Contractor/Manufacturer | Engineer | upon installation | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=510-7.5
Manufacturer's Written Certification (Concrete Barriers, Traffic Railing Barriers & Parapets) | 521-1 | Link | Manufacturer | Engineer | each shipment to the job-site | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 521 Concrete Barrier Wall&QPLDesc=Delineator - Barrier Wall&QPLNum=S521 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=521-1
Certification (Precast temporary barrier wall) | 521-3.2 | Link | Manufacturer | Engineer | upon use | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 521 Concrete Barrier Wall&QPLDesc=Delineator - Barrier Wall&QPLNum=S521 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=521-3.2
Certification (Patterned/Textured Pavement) | 523-3.3 | Link | Contractor | Engineer | Upon installation | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 523 Patterned Pavement&QPLDesc=Patterned Pavement&QPLNum=S523 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=523-3.3
Product Certification (Sound Barriers) | 534-5 | Link | Contractor/Manufacturer | Engineer | upon installation | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 534 Noise Barrier Wall&QPLDesc=Sound Barrier System&QPLNum=S534 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=534-5
Manufacturer's Certification (Guardrail/Steel Posts) | 536-2.2.3 | Link | Contractor/Manufacturer | Engineer | Upon use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=536-2.2.3
Manufacturer's Certification (Guardrail construction) | 536-2.6 | Link | Contractor/Manufacturer | Engineer | At least 10 days prior to guardrail construction | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=536-2.6
Written Certification (Retaining Wall Systems) | 548-1 | Link | Contractor/Manufacturer | Engineer | Upon use | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 548 Retaining Wall Systems&QPLDesc=Retaining Wall System&QPLNum=S548 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=548-1
Certification (Retaining Wall Systems/Backfill Material) | 548-2.6 | Link | Contractor | Engineer | Prior to Placement | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=548-2.6
Certification (Retaining Wall Systems) | 548-8 | Link | Contractor | Engineer | at least 10 days prior to wall construction | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=548-8
Certification (Fencing) | 550-3.6 | Link | Contractor | Engineer | at least 10 days prior to fence construction | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=550-3.6
Certification (Bonded Fiber Matrix(BFM)) | 570-3.5 | Link | Contractor/grower | Engineer | 7 calendar days prior to installation | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=570-3.5
Certification (Landscape Installation) | 580-2.1.1 | Link | Contractor/Nurseryman Stock | Engineer | prior to planting | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=580-2.1.1
Manufacturer's Certifications (Acceptance Procedures/Manufacturer's Test and Certifications) | 611-6 | Link | Contractor | Engineer | Upon request | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=611-6
Accepting of Signs by Certification (Internally Illuminated Signs) | 699-3.1 | Link | Contractor | Engineer | After placement | APL | Link |  | http://www3.dot.state.fl.us/trafficcontrolproducts/ | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=699-3.1
Manufacturer's Certification (Highway Signing) | 700-6.1 | Link | Sign Manufacturer/Producer | Engineer | Upon Receipt | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=700-6.1
Manufacturer's Certification (Highway Signing/Sign Inspection) | 700-6.4 | Link | Contractor/Manufacturer | Engineer | Prior to Engineer's Inspection | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=700-6.4
Certification (Retroreflectivity) | 701-4.4 | Link | Contractor | Engineer | After placement | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 701 Audible and Vibratory Pavement Markings&QPLDesc=Audible and Vibratory Pavement Markings&QPLNum=S701 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=701-4.4
Certification of Quantities | 701-9.2 | Link | Contractor | Engineer | No later than 12 O'clock noon Monday after the estimate cut-off or as directed by the engineer | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=701-9.2
Manufacturer's Certification (Highway Delineators) | 705-2.2 | Link | Contractor/Manufacturer | Engineer | After placement | QPL - Type A | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 706 Raised Retro-Reflective Pavement Markers and Bituminous Adhesive&QPLDesc=Raised Pavement Marker Class A&QPLNum=S706 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=705-2.2
[6 empty] | QPL - Type B | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 706 Raised Retro-Reflective Pavement Markers and Bituminous Adhesive&QPLDesc=Raised Pavement Marker Class B&QPLNum=S706 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=
Manufacturer's Certification (Raised Retro-Reflective Pavement Markers & Bituminous Adhesive) | 706-2.1 | Link | Contractor/Manufacturer | Engineer | After placement | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 706 Raised Retro-Reflective Pavement Markers and Bituminous Adhesive&QPLDesc=Raised Pavement Marker Adhesive&QPLNum=S706 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=706-2.1
Traffic Stripes and Markings - Two Reactive Components | 709-4.3 | Link | Contractor | Engineer | After placement | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 709 Traffic Stripes and Markings - Two Reactive Components&QPLDesc=Two Reactive Component Traffic Marking&QPLNum=S709 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=709-4.3
Contractor's Certification (Retroreflectivity) | 710-4.3 | Link | Contractor | Engineer | Upon use | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 710 Painting Traffic Stripes&QPLDesc=Water Base Traffic Paint&QPLNum=S710 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=710-4.3
Contractor's Certification of Quantities (Painted Pavement Markings) | 710-9.2 | Link | Contractor | Engineer | No later than 12 O'clock noon Monday after the estimate cut-off or as directed by the engineer | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 710 Painting Traffic Stripes&QPLDesc=Water Base Traffic Paint&QPLNum=S710 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=710-9.2
Contractor's Certification (Thermoplastic Traffic Stripes and Markings-Retroreflectivity) | 711-4.3 | Link | Contractor | Engineer | Upon use | QPL | Link |  | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=711-4.3
Certification of Quantities | 713-9.2 | Link | Contractor | Engineer | No later than 12 O'clock noon Monday after the estimate cut-off or as directed by the engineer | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 713 Preformed Pavement Stripes and Markings&QPLDesc=Permanent Tape High Performance&QPLNum=S713 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=713-9.2
Division III Specifications
Certification on the bill of Lading (PG Binder) | 916-1.3.6 | Link | Supplier | Engineer | Upon Receipt | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 916 Bituminous Materials&QPLDesc=Super Pave Asphalt Binder&QPLNum=S916 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=916-1.3.6
Certification on the bill of Lading (Recycling Agent) | 916-2.3 | Link | Supplier | Engineer | Upon Receipt | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 916 Bituminous Materials&QPLDesc=Anti-Strip agent&QPLNum=S916 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=916-2.3
Certification (Ground tire Rubber) | 919-6 | Link | Contractor | Engineer | Upon Receipt | QPL - A | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 919 Ground Tire Rubber For Use In Asphalt Rubber Binder&QPLDesc=Ground Tire Rubber Type A&QPLNum=S919
[6 empty] | QPL - B | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 919 Ground Tire Rubber For Use In Asphalt Rubber Binder&QPLDesc=Ground Tire Rubber Type B&QPLNum=S919
[6 empty] | QPL - C | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 919 Ground Tire Rubber For Use In Asphalt Rubber Binder&QPLDesc=Ground Tire Rubber Type C&QPLNum=S919 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=919-6
Cement Mill Analysis Certification (Portland Cement) | 921-5.1 | Link | Contractor | Engineer | Upon Receipt | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=921-5.1
Certification Test Results (Portland Cement) | 921-5.2 | Link | Contractor | District Materials Office | Upon Request | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=921-5.2
Certification of Test Results (Admixtures of Concrete) | 924-2.2 | Link | Manufacturer | Engineer | Upon Request | QPL | Link |  | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=924-2.2
Certification (Burlap) | 925-4 | Link | Contractor | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=925-4
Manufacturer's Certification (Epoxy Compounds) | 926-2.3 | Link | Contractor | Engineer | Prior to use | QPL | Link | Yes | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=926-2.3
Certification (Fly Ash) | 929-2.6 | Link | Supplier | State Materials Office | Upon use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=929-2.6
Certification (Silica Fume) | 929-3.2 | Link | Supplier | State Materials Office | Upon use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=929-3.2
Certification (Metakaolin) | 929-4.2 | Link | Supplier | State Materials Office | Upon use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=929-4.2
Certification (Slag) | 929-5.4 | Link | Supplier | State Materials Office | Upon use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=929-5.4
Certification (Ultra Fine Fly Ash) | 929-6.3 | Link | Supplier | State Materials Office | Upon use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=929-6.3
Certification (Materials for Concrete Repair) | 930-2.1 | Link | Manufacturer | Engineer | Upon use | QPL | Link |  | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=930-2.1
Certification (Reinforcing Steel) | 931-1.1 | Link | Contractor | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=931-1.1
Certification (Sheet Metal Bottom Strips) | 931-2.1 | Link | Contractor | Engineer | Upon use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=931-2.1
Certification (Dowel Bars) | 931-2.3 | Link | Contractor | Engineer | Upon Receipt | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=931-2.3
Certification (Preformed Joint Filler) | 932-1.1.1 | Link | Contractor | Engineer | Prior to use | QPL | Link | Yes | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=932-1.1.1
Certification (Joint Sealer Material) | 932-1.2.3 | Link | Contractor | Engineer | Prior to use | QPL | Link | Yes | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=932-1.2.3
Certification (Bearing Pads) | 932-2.3 | Link | Contractor | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=932-2.3
Certification (Prestressing) | 933-5.2 | Link | Manufacturer | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=933-5.2
Certification (Adhesive Bonding Material System) | 937-3 | Link | Manufacturer | Engineer | Prior to use | QPL - HV | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 937 Adhesive Bonding Material Systems For Structural Applications&QPLDesc=Structural Adhesive Bonding Compound Type HV&QPLNum=S937 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=937-3
[6 empty] | QPL -HSHV | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 937 Adhesive Bonding Material Systems For Structural Applications&QPLDesc=Structural Adhesive Bonding Compound Type HSHV&QPLNum=S937
Certification (Gasket Material) | 942-2.3 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 942 Pipe Gaskets&QPLDesc=Resilient connector&QPLNum=S942 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=942-2.3
Certification (Actual Mean Diameter of the Pipe) | 943-1 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=943-1
Certification (Actual Mean Diameter of the Pipe-Corrugated Aluminum-Alloy Culverts & Underdrains) | 945-1 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=945-1
Certification of Test Results (Aluminum Materials) | 945-2.3 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=945-2.3
Certification (Acutal Mean Diameter of the Pipe-PVC | 948-1.7 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=948-1.7
Certification (Actual mean diameter of the Pipe-Corrugated Polyethylene Pipe) | 948-2.3.1 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=948-2.3.1
Certification (Each Pipe Diameter-Corrugated Polyethylene Pipe) | 948-2.3.3 | Link | Manufacturer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=948-2.3.3
Certification (Treatment-Inspection of Timber Products) | 951-2 | Link | Producer | Engineer | Prior to Requesting Inspection | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=951-2
Certifcation of Compliance (Inspection of Timber Products) | 951-3 | Link | Producer | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=951-3
Certification (all metal materials) | 962-10 | Link | Contractor | Engineer | Prior to use | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=962-10
Certification (General Provisions for Aluminum Items Including Welding) | 965-2 | Link | Producer | State Materials Office | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=965-2
Certification (Rail Elements for Guardrail) | 967-1 | Link | Manufacturer | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=967-1
Certification (Structural Plastics) | 973-2 | Link | Manufacturer | Engineer | Prior to use | QPL - | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 973 Structural Plastic &QPLDesc=Structural Plastic FFRCL (Lumber)&QPLNum=S973
[6 empty] | QPL - | Link | Yes | http://www2.dot.state.fl.us/SpecificationsEstimates/ProductEvaluation/QPL/QPLItems.aspx?QPLTitle=Specification 973 Structural Plastics&QPLDesc=Structural Plastic SCL (Wales)&QPLNum=S973 | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=973-2
Certification (Structural Coating) | 975-3.1 | Link | Contractor | Engineer | Prior to use | QPL |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=975-3.1
Certification (Turf Material) | 981-1 | Link | Contractor/FDOACS | Engineer | Upon Delivery | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=981-1
Certification (Sod Condition) | 981-3.3 | Link | Turf Contractor | Engineer | Upon Delivery | Neither |  |  |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=981-3.3
Certification (Fertilizer) | 982-2 | Link | Contractor/Manufacturer | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=982-2
Certification (Geotextile Fabrics) | 985-4 | Link | Manufacturer | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=985-4
Certification (Sheeting for Temp Traffic Control Devices) | 990-2 | Link | Manufacturer | Engineer | Prior to use | QPL | Link |  | http://www.dot.state.fl.us/specificationsoffice/ProductEvaluation/QPL/QPLMOTIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=990-2
Certification (Luminaires, Ballasts) | 992-4.2 | Link | Contractor | Engineer | Prior to use | Neither |  | Yes |  | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=992-4.2
Certification (Retroreflective & Nonretroreflective sign sheeting) | 994-7 | Link | Contractor | Engineer | Prior to use | QPL | Link | Yes | http://www.dot.state.fl.us/SpecificationsOffice/ProductEvaluation/QPL/QPLIndex.shtm | ftp://ftp.dot.state.fl.us/LTS/CO/Specifications/SpecBook/2010Book/2010Master.pdf#search=994-7