## LEGAL REQUIREMENTS AND RESPONSIBILITY TO THE PUBLIC – OPERATIONS WITHIN THE RAILROAD RIGHT-OF-WAY.

(REV 3-11-16) (FA 8-2-16) (1-17)

SUBARTICLE 7-11.4 is deleted and the following substituted:

7-11.4 Operations Within Railroad Right-of-Way:

7-11.4.1 Notification to the Railroad Company:

7-11.4.1.1 CSX Transportation (CSXT), Norfolk Southern (NS), and Department-Owned Rail Corridors: Submit written notification to the Engineer at least 72 hours before beginning any operation within the limits of the railroad right-of-way; any operation requiring movement of employees, trucks, or other equipment across the tracks of the railroad company at other than an established public crossing; and any other work that may affect railroad operations or property.

7-11.4.1.2 Florida East Coast Railway (FEC): Submit written notification to the Chief FEC Engineer or authorized Railway Representative at least 72 hours before beginning any operation within the limits of the railroad right-of-way; any operation requiring movement of employees, trucks, or other equipment across the tracks of the railroad company at other than an established public crossing; and any other work that may affect railroad operations or property.

Contact the FEC Signal Office at 904-279-3182 at least 30 days prior to any traffic signal work within 500 feet of a signalized, at-grade, rail-highway crossing.

7-11.4.2 Contractor’s Responsibilities: Comply with requirements deemed necessary by the railroad company’s authorized representative to safeguard the railroad’s property and operations. Do not perform temporary lane closures, lane shifts or detour routes within the railroad company right-of-way without railroad approval.

The Contractor is responsible for all damages, delays, or injuries and all suits, actions, or claims brought on account of damages or injuries resulting from the Contractor’s operations within or adjacent to railroad company right-of-way.

7-11.4.2.1 CSXT: Comply with the Construction Submission Criteria of the CSXT Public Project Information document and Construction Requirements sections of the CSXT Pipeline and Wireline Design and Construction Specifications prior to beginning work. These documents are available at the following URL: http://www.dot.state.fl.us/programmanagement/Implemented/URLinSpecs/CSXT.shtm.

Perform no work within the limits of the railroad right-of-way on CSXT holidays. CSXT holidays are New Year’s Day, President’s Day, Good Friday, Memorial Day, Independence Day, Labor Day, Thanksgiving Day and the following Friday, Christmas Eve, Christmas Day, and New Year’s Eve. Holidays falling on Saturday are observed on Friday and those falling on Sunday are observed on Monday.

7-11.4.2.2 NS: Comply with the NS Special Provisions for Protection of Railway Interests (Appendix E) and the Construction Requirements (Appendix 4.3) of the NS Public Projects Manual document prior to beginning and during all work. These documents are available at the following URL: http://www.nscorp.com/content/dam/nscorp/ship/shipping-tools/Public_Projects_Manual.pdf.

7-11.4.2.3 FEC: Complete the On-Track Contractor Roadway Worker Training Course for FEC Railway. Contact FEC Railway at 1-800-342-1131 for training information.

Costs incurred by the railroad for Contractor caused delays that adversely impact railway operations will be forwarded to the Contractor for payment. If the Contractor fails to pay said costs, the Department will deduct the amount from payments to be made to the Contractor.

7-11.4.3 Watchman or Flagging Services:

7-11.4.3.1 CSXT, NS, and FEC:

7-11.4.3.1.1 General: The railroad company will furnish protective services (i.e., watchman or flagging services) to ensure the safety of railroad operations during certain periods of the project. The Department will reimburse the railroad company for the cost thereof. Schedule work that affects railroad operations so as to minimize the need for protective services by the railroad company.

7-11.4.3.1.2 CSXT: Submit schedules and schedule changes to the Engineer so the Department can coordinate the scheduling of flagging resources. Projects with less than 20 consecutive days of flagging services require a CSXT short-term flagger and 45 days written advance notice. Submit the 45 days written advance notice to the Engineer. Projects with 20 or more consecutive days of flagging services require a CSXT long term flagger. The Department will submit the 6 months written advance notice to CSXT.

7-11.4.3.1.3 NS: Submit schedules and schedule changes to the Engineer so the Department can coordinate the scheduling of flagging resources. Projects with less than 20 consecutive days of flagging services require a NS short-term flagger and 45 days written advance notice. Submit the 45 days written advance notice to the Engineer. Projects with 20 or more consecutive days of flagging services require a NS long term flagger. The Department will submit the 6 months written advance notice to NS.

7-11.4.3.1.4 FEC: Contact FEC Railway at 1-800-342-1131, ext. 2377, to request signal locates and railroad watchmen or flagging services at least 72 hours prior to railroad right-of-way encroachments. When requesting railroad watchman or flagging services, identify the work as a Florida Department of Transportation project.

7-11.4.3.2 Department-Owned Rail Corridors: The Department will furnish protective services (i.e., watchman or flagging services) to ensure the safety of railroad operations during certain periods of the project.

For projects involving the South Florida Rail Corridor (SFRC), contact the South Florida Regional Transportation Authority (SFRTA) at 954-788-1788 at least 30 days prior to rail corridor right-of-way encroachments to coordinate the scheduling of flagging resources.

For projects involving the Central Florida Rail Corridor (CFRC), submit written advance notice to the Engineer at least 30 days prior to rail corridor right-of-way encroachments so the Department can coordinate the scheduling of flagging resources.