## TML Guidelines
Task No. | Task | Units | Range Catagories | [8 empty] | Basis for Staff Hour Range
30.01 | Terrestrial Mobile LiDAR Mission Planning |  | 2-Lane Roadway |  |  | Multi-Lane / Interstate |  |  | Urban
| Choose Range Category | Scan Miles | 0 | - | 0.1 | 0 | - | 0.15 | 0 | - | 0.4 | All efforts necessary for planning and preparation of materials needed for the successful execution of the Mobile LiDAR Mission. Includes route and safety planning; GPS /data acquisition scheduling, weather reports, and site terrain research.
|  | Scan Miles | 0 | - | 0.5 | 0 | - | 0.8 | 0 | - | 1
|  | Scan Miles | 0 | - | 0.5 | 0 | - | 0.8 | 0 | - | 1
30.02 | Project Control Point Coordination
| Choose Range Category | Point | 0 | - | 0.02 | 0 | - | 0.05 | 0 | - | 0.1 | All efforts necessary to coordinate the proper placement of project ground control i.e. base stations, transformation control points, and validation points, supporting the Mobile LiDAR survey. Includes communication of appropriate accuracies along with of target specifications and identification with field and office personnel.
|  | Point | 0 | - | 0.04 | 0 | - | 0.08 | 0 | - | 0.2
|  | Point | 0 | - | 0.04 | 0 | - | 0.08 | 0 | - | 0.2
30.03 | Terrestrial Mobile LiDAR Mobilization
| Choose Range Category | Personnel | [9 empty] | Includes cost to get specialized personnel and equipment on site. When additional field personnel are needed for safety etc. during scan, the additional # of staff should be entered into No. of Units column.
Personnel
30.04 | Terrestrial Mobile LiDAR Mission
| Choose Range Category | Scan Miles | 0 | - | 0.2 | 0 | - | 0.3 | 0 | - | 0.4 | Includes on site calibration, collection of Mobile LiDAR data, and any simultaneous base station occupations. Personnel should include any safety or supporting personnel if necessary.
|  | Scan Miles | 0 | - | 0.2 | 0 | - | 0.3 | 0 | - | 0.4
30.05 | Terrestrial Mobile LiDAR Processing
| Choose Range Category | Scan Miles | 0 | - | 0.1 | 0 | - | 0.1 | 0 | - | 0.2 | Includes downloading and post processing of Global Navigation Satellite System (GNSS) / Inertial Navigation System (INS) data, creation of scan vehicle best estimate trajectories, analysis of scan route data overlaps. Also includes if necessary, separation of large point cloud data sets into manageable LAS (see ASPRS) files with corresponding graphic "tile" index.
|  | Scan Miles | 0 | - | 0.4 | 0 | - | 1 | 0 | - | 0.5
|  | Scan Miles | 0 | - | 0.6 | 0 | - | 0.7 | 0 | - | 0.8
30.06 | Terrestrial Mobile Photography Processing
| Choose Range Category | Scan Miles | 0 | - | 0.03 | 0 | - | 0.04 | 0 | - | 0.06 | Includes the formatting, organizing, and naming digital photographic imagery (if any) collected during Mobile LiDAR mission. If adjustment or rectification is needed this will result in significantly higher range values, and may even need to be specified elsewhere in tab 28.
|  | Scan Miles | 0 | - | 0.1 | 0 | - | 0.2 | 0 | - | 0.3
|  | Scan Miles | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 2
30.07 | Transformation / Adjustment
| Choose Range Category | Scan Miles | 0 | - | 0.4 | 0 | - | 0.6 | 0 | - | 1 | Includes transformation / Adjustment of LiDAR point cloud to Project Control, accuracy analysis, NSSDA reporting of validation points, and includes cross section analysis. If this is performed by separate firm or is the final product delivered, it should be accompanied by a Survey Report certifying accuracy and meeting MTS . Also includes creation and delivery of adjusted point cloud data in digital LAS (see ASPRS) file(s) format.
|  | Scan Miles | 0 | - | 1 | 0 | - | 1.5 | 0 | - | 2
|  | Scan Miles |  | - |  |  | - |  |  | -
30.08 | Classification / Editing |  | 2-Lane Roadway |  |  | Multi-Lane / Interstate |  |  | Urban
| Choose Range Category | Corridor Miles | 0 | - | 0.4 | 0 | - | 0.6 | 0 | - | 0.8 | Includes any classification of point cloud data, removal or classification of anomalies from such things as moving object ghosting, erroneous point returns, points outside effective range of sensor, etc. These task ranges will vary significantly depending on number of classification categories required by project scope.
|  | Corridor Miles | 0 | - | 2 | 0 | - | 5 | 0 | - | 5
|  | Corridor Miles | 0 | - | 2 | 0 | - | 5 | 0 | - | 10
30.09 | Specific Surface Reporting
| Choose Range Category | Corridor Miles | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes reporting of specific surface details such as pavement rutting, bridge structure clearance to roadway surface. This task is used for efforts NOT covered under other typical topographic mapping tasks.
|  | Corridor Miles | 0 | - | 1 | 0 | - | 2 | 0 | - | 5
|  | Corridor Miles | 0 | - | 2 | 0 | - | 3 | 0 | - | 10
30.1 | Topographic (3D) Mapping
| Choose Range Category | Corridor Miles | 0 | - | 0.3 | 0 | - | 0.5 | 0 | - | 1 | Includes efforts necessary to produce three dimensional (3D) topographic survey map from collected Mobile LiDAR data. Do not duplicate effort for project areas that may be covered under 30.11 Topographic (2D) Planimetric Mapping.
|  | Corridor Miles | 0 | - | 15 | 0 | - | 20 | 0 | - | 30
|  | Corridor Miles | 0 | - | 25 | 0 | - | 30 | 0 | - | 40
30.11 | Topographic (2D) Planimetric Mapping
| Choose Range Category | Corridor Miles | 0 | - | 0.3 | 0 | - | 0.4 | 0 | - | 0.6 | Includes efforts necessary to produce two dimensional (2D) planimetric survey map from collected Mobile LiDAR data. Do not duplicate effort for project areas that may be covered under 30.10 Topographic (3D) Mapping.
|  | Corridor Miles | 0 | - | 0.5 | 0 | - | 0.6 | 0 | - | 0.8
|  | Corridor Miles | 0 | - | 3 | 0 | - | 5 | 0 | - | 6
30.12 | CADD Edits
| Choose Range Category | Corridor Miles | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes CADD edit of graphics after field review for delivery of required electronic files. (MicroStation .dgn, CADD)
|  | Corridor Miles | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 1
|  | Corridor Miles | 0 | - | 2 | 0 | - | 4 | 0 | - | 6
30.13 | Data Merging
| Choose Range Category | Corridor Miles | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes final edit of graphics for delivery after ingesting outlying or obscured areas measured with other technologies. (MicroStation .dgn, CADD and Geopak files.)
|  | Corridor Miles | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 1
|  | Corridor Miles | 0 | - | 1 | 0 | - | 2 | 0 | - | 7
30.14 | Miscellaneous
|  | LS | [9 empty] | For miscellaneous tasks not covered on spreadsheet sepcific tasks. The # of staff should be entered into No. of Units column.
LS
LS
LS
LS
30.15 | Field Reviews
|  | LS | [9 empty] | Includes site visit and "walk through" as part of quality assurance by P.S.M.(s) responsible for survey map data and products.
LS
30.16 | Technical Meetings
|  | LS | [9 empty] | LS based on average number of people per meeting x length of meeting x number of meetings. Length of meeting includes travel time for scheduled meetings.
30.17 | Quality Assurance / Quality Control
|  | LS | [9 empty] | Includes implementation of QA / QC plan. Also includes sub consultant review, response to comments and any resolution meetings if required, preparation of submittals for review, etc. (LS based on 5 - 7% of technical tasks)
30.18 | Supervision
|  | LS | [9 empty] | Includes effort required to supervise Terrestrial Mobile LiDAR mapping project activities. These activities must be performed by the project supervisor, a Florida P.S.M. (LS based on 5 - 7% from tasks 5 through 23, where applicable.)
30.19 | Coordination
|  | LS | [9 empty] | Includes efforts of the Terrestrial Mobile LiDAR surveyor responsible for the survey project deliverables to coordinate with the other surveyors 9if any) on the final presentation of survey map/report after data merging, communicating each surveyor's responsibility with the Department's Project Manager with (LS based on 2-3% of all the above tasks).
30. Terrestrial Mobile LiDAR Mapping Total

## 30. Terrestrial Mobile LiDAR
| Task | Units | No. of Units | Hour / Unit | Hours | Hours | Hours | Hours | Hours | Total Range
Task No. |  |  |  |  | PSM | Senior LiDAR Technician | LiDAR Technician | LiDAR Operator | Field Technician |  | Comments | Range Catagories | [8 empty] | Basis for Staff Hour Range
30.01 | Terrestrial Mobile LiDAR Mission Planning |  | Terrestrial Mobile LiDAR Mission Planning | [8 empty] | 2-Lane Roadway |  |  | Multi-Lane / Interstate |  |  | Urban
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.1 | 0 | - | 0.15 | 0 | - | 0.4 | All efforts necessary for planning and preparation of materials needed for the successful execution of the Mobile LiDAR Mission. Includes route and safety planning; GPS /data acquisition scheduling, weather reports, and site terrain research.
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.5 | 0 | - | 0.8 | 0 | - | 1
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 0.5 | 0 | - | 0.8 | 0 | - | 1
30.02 | Project Control Point Coordination |  | Control Point Coordination
| Choose Range Category | Point | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.02 | 0 | - | 0.05 | 0 | - | 0.1 | All efforts necessary to coordinate the proper placement of project ground control i.e. base stations, transformation control points, and validation points, supporting the Mobile LiDAR survey. Includes communication of appropriate accuracies along with of target specifications and identification with field and office personnel.
|  | Point | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.04 | 0 | - | 0.08 | 0 | - | 0.2
|  | Point | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 0.04 | 0 | - | 0.08 | 0 | - | 0.2
30.03 | Terrestrial Mobile LiDAR Mobilization |  | Terrestrial Mobile LiDAR Mobilization
| Choose Range Category | Personnel | 1 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only | [9 empty] | Includes cost to get specialized personnel and equipment on site. When additional field personnel are needed for safety etc. during scan, the additional # of staff should be entered into No. of Units column.
|  | Personnel | 2 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
30.04 | Terrestrial Mobile LiDAR Mission |  | Terrestrial Mobile LiDAR Mission
| Choose Range Category | Scan Miles | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Sensor Operator | 0 | - | 0.2 | 0 | - | 0.3 | 0 | - | 0.4 | Includes on site calibration, collection of Mobile LiDAR data, and any simultaneous base station occupations. Personnel should include any safety or supporting personnel if necessary.
|  | Scan Miles | 0 | 0 | Number of Field Technician(s) = |  |  | 2 | 0 | 0 | 1-Technician to drive vehicle , 1-base station | 0 | - | 0.2 | 0 | - | 0.3 | 0 | - | 0.4
30.05 | Terrestrial Mobile LiDAR Processing |  | Terrestrial Mobile LiDAR Processing
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.1 | 0 | - | 0.1 | 0 | - | 0.2 | Includes downloading and post processing of Global Navigation Satellite System (GNSS) / Inertial Navigation System (INS) data, creation of scan vehicle best estimate trajectories, analysis of scan route data overlaps. Also includes if necessary, separation of large point cloud data sets into manageable LAS (see ASPRS) files with corresponding graphic "tile" index.
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.4 | 0 | - | 1 | 0 | - | 0.5
|  | Scan Miles | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator | 0 | - | 0.6 | 0 | - | 0.7 | 0 | - | 0.8
30.06 | Terrestrial Mobile Photography Processing |  | Terrestrial Mobile Photography Processing
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.03 | 0 | - | 0.04 | 0 | - | 0.06 | Includes the formatting, organizing, and naming digital photographic imagery (if any) collected during Mobile LiDAR mission. If adjustment or rectification is needed this will result in significantly higher range values, and may even need to be specified elsewhere in tab 28.
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.1 | 0 | - | 0.2 | 0 | - | 0.3
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 2
30.07 | Transformation / Adjustment |  | Transformation / Adjustment
| Choose Range Category | Scan Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.4 | 0 | - | 0.6 | 0 | - | 1 | Includes transformation / Adjustment of LiDAR point cloud to Project Control, accuracy analysis, NSSDA reporting of validation points, and includes cross section analysis. If this is performed by separate firm or is the final product delivered, it should be accompanied by a Survey Report certifying accuracy and meeting MTS . Also includes creation and delivery of adjusted point cloud data in digital LAS (see ASPRS) file(s) format.
|  | Scan Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 1 | 0 | - | 1.5 | 0 | - | 2
|  | Scan Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only |  | - |  |  | - |  |  | -
30.08 | Classification / Editing |  | Classification / Editing | [8 empty] | 2-Lane Roadway |  |  | Multi-Lane / Interstate |  |  | Urban
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.4 | 0 | - | 0.6 | 0 | - | 0.8 | Includes any classification of point cloud data, removal or classification of anomalies from such things as moving object ghosting, erroneous point returns, points outside effective range of sensor, etc. These task ranges will vary significantly depending on number of classification categories required by project scope.
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 2 | 0 | - | 5 | 0 | - | 5
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 2 | 0 | - | 5 | 0 | - | 10
30.09 | Specific Surface Reporting |  | Specific Surface Reporting
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes reporting of specific surface details such as pavement rutting, bridge structure clearance to roadway surface. This task is used for efforts NOT covered under other typical topographic mapping tasks.
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 1 | 0 | - | 2 | 0 | - | 5
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 2 | 0 | - | 3 | 0 | - | 10
30.1 | Topographic (3D) Mapping |  | Topographic (3D) Mapping
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.3 | 0 | - | 0.5 | 0 | - | 1 | Includes efforts necessary to produce three dimensional (3D) topographic survey map from collected Mobile LiDAR data. Do not duplicate effort for project areas that may be covered under 30.11 Topographic (2D) Planimetric Mapping.
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 15 | 0 | - | 20 | 0 | - | 30
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 25 | 0 | - | 30 | 0 | - | 40
30.11 | Topographic (2D) Planimetric Mapping |  | Topographic (2D) Planimetric Mapping
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.3 | 0 | - | 0.4 | 0 | - | 0.6 | Includes efforts necessary to produce two dimensional (2D) planimetric survey map from collected Mobile LiDAR data. Do not duplicate effort for project areas that may be covered under 30.10 Topographic (3D) Mapping.
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.5 | 0 | - | 0.6 | 0 | - | 0.8
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 3 | 0 | - | 5 | 0 | - | 6
30.12 | CADD Edits |  | CADD Edits
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes CADD edit of graphics after field review for delivery of required electronic files. (MicroStation .dgn, CADD)
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 1
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 2 | 0 | - | 4 | 0 | - | 6
30.13 | Data Merging |  | Data Merging
| Choose Range Category | Corridor Miles | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | 0 | - | 0.2 | 0 | - | 0.4 | 0 | - | 0.5 | Includes final edit of graphics for delivery after ingesting outlying or obscured areas measured with other technologies. (MicroStation .dgn, CADD and Geopak files.)
|  | Corridor Miles | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only | 0 | - | 0.5 | 0 | - | 1 | 0 | - | 1
|  | Corridor Miles | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Technician Only | 0 | - | 1 | 0 | - | 2 | 0 | - | 7
30.14 | Miscellaneous
| Survey Report | LS | 0 | 0 | 0 |  |  |  |  | 0 | PSM Only | [9 empty] | For miscellaneous tasks not covered on spreadsheet sepcific tasks. The # of staff should be entered into No. of Units column.
|  | LS | 0 | 0 |  | 0 |  |  |  | 0 | Sr. LiDAR Tech Only
|  | LS | 0 | 0 |  |  | 0 |  |  | 0 | LiDAR Tech Only
|  | LS | 0 | 0 |  |  |  | 0 |  | 0 | LiDAR Operator Only
|  | LS | 0 | 0 |  |  |  |  | 0 | 0 | Field Technician Only
|  |  | Mobile Scan Technical Subtotal | [6 empty] | 0
30.15 | Field Reviews
|  | LS | 0 |  | 0 |  |  |  |  | 0 | [10 empty] | Includes site visit and "walk through" as part of quality assurance by P.S.M.(s) responsible for survey map data and products.
|  | LS | 0 |  |  | 0 |  |  |  | 0
30.16 | Technical Meetings
|  | LS | [7 empty] | 0 | From Meetings Table Below (i93) | [9 empty] | LS based on average number of people per meeting x length of meeting x number of meetings. Length of meeting includes travel time for scheduled meetings.
30.17 | Quality Assurance / Quality Control
|  | LS | 7% | [6 empty] | 0 | [10 empty] | Includes implementation of QA / QC plan. Also includes sub consultant review, response to comments and any resolution meetings if required, preparation of submittals for review, etc. (LS based on 5 - 7% of technical tasks)
30.18 | Supervision
|  | LS | 7% | [6 empty] | 0 | [10 empty] | Includes effort required to supervise Terrestrial Mobile LiDAR mapping project activities. These activities must be performed by the project supervisor, a Florida P.S.M. (LS based on 5 - 7% from tasks 5 through 23, where applicable.)
|  |  | Mobile Scan Nontechnical Subtotal | [6 empty] | 0
30.19 | Coordination
|  | LS | 2% | [6 empty] | 0 | [10 empty] | Includes efforts of the Terrestrial Mobile LiDAR surveyor responsible for the survey project deliverables to coordinate with the other surveyors 9if any) on the final presentation of survey map/report after data merging, communicating each surveyor's responsibility with the Department's Project Manager with (LS based on 2-3% of all the above tasks).
30. Terrestrial Mobile LiDAR Mapping Total | [9 empty] | 0
* The low end of the range is for rural 2-lane; medium range is for typical Multi-Lane; the high end of the range is for urban/interstate.
| Technical Meetings |  |  | # of Units |  | Hours | Total Hrs.
| Terrestrial Mobile LiDAR Mapping Submittal Review |  | EA | 0 |  | 0 | 0
| Other Meetings |  | EA | 0 |  | 0 | 0
| Subtotal Technical Meetings | [5 empty] | 0 | Hours
| Progress Meetings |  | EA | 0 |  | 0 | 0
| Phase Review Meetings |  | EA | 0 |  | 0 | 0
| Total Meeting Hours | [5 empty] | 0 | Hours
Carries to 30.16
PM Attendance at Meeting Required?
| Yes / No | Number
| no | 0
| no | 0
Project manager meetings =
|  | 0 | Carries to Task 3, Project General